## novalex_submission_tracker_upda
Unique Submission ID | Trigger ID | Submission Title | Product Name | Submission Category | Variation Category | Related Safety Signal (if any) | Submission Status | Priority | Risk Level | Planned Submission Date | Actual Submission Date | Approval Decision Date | Target Implementation Date | Actual Implementation Date | Functional Owner | Safety Labeling Change (SLC) Required
NVX-SUB-001 | TRG-001 | Change in the name and/or address of the marketing authorisation holder | Novalex | Administrative | IAIN |  | Archived | Medium | Low/Medium | 2024-06-15 | 2024-06-15 | 2024-07-15 | 2024-06-17 | 2024-06-17 | Regulatory Operations / Regulatory Affairs | No
NVX-SUB-002 | TRG-002 | Change in the (invented) name of the medicinal product - a) for Centrally Authorised products | Novalex | Administrative | IAIN |  | Archived | Medium | Low/Medium | 2024-06-29 | 2024-07-01 | 2024-07-31 | 2024-07-03 | 2024-07-03 | Regulatory Operations / Regulatory Affairs | No
NVX-SUB-003 | TRG-004 | Change in name of the active substance or of an excipient | Novalex | Administrative | IAIN |  | Archived | Medium | Low/Medium | 2024-07-13 | 2024-07-14 | 2024-08-13 | 2024-07-16 | 2024-07-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-004 | TRG-005 | Change in the name and/or address of: a manu facturer (including where relevant quality control testing sites); or an ASMF holder; or a supplier of the active s | Novalex | Administrative | IA |  | Archived | Low | Low | 2024-07-01 | 2024-07-05 | 2024-08-04 | 2024-11-18 | 2024-12-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-005 | TRG-006 | Change in the name and/or address of a manufac turer/importer of the finished product (including batch release or quality control testing sites) - a) The activi | Novalex | Administrative | IAIN |  | Archived | Medium | Low/Medium | 2024-07-27 | 2024-07-27 | 2024-08-26 | 2024-07-30 | 2024-08-06 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-006 | TRG-007 | Change in the name and/or address of a manufac turer/importer of the finished product (including batch release or quality control testing sites) - b) The activi | Novalex | Administrative | IA |  | Archived | Low | Low | 2024-07-11 | 2024-07-13 | 2024-08-12 | 2024-09-18 | 2024-10-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-007 | TRG-008 | Change in ATC Code/ATC Vet Code | Novalex | Administrative | IA |  | Archived | Low | Low | 2024-07-21 | 2024-07-23 | 2024-08-22 | 2024-11-16 | 2024-12-01 | Regulatory Operations / Regulatory Affairs | No
NVX-SUB-008 | TRG-009 | Deletion of manufacturing sites for an active substance, intermediate or finished product, packaging site, manufacturer responsible for batch release, site wher | Novalex | Administrative | IA |  | Archived | Low | Low | 2024-07-31 | 2024-08-02 | 2024-09-01 | 2024-10-21 | 2024-11-15 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-009 | TRG-010 | Changes to date of the audit to verify GMP compliance of the manufacturer of the active substance (*) | Novalex | Administrative | IA |  | Archived | Low | Low | 2024-08-10 | 2024-08-10 | 2024-09-09 | 2024-10-22 | 2024-11-15 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-010 | TRG-011 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process of the active substance or change in the manufacturer | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2026-01-15 | 2026-01-16 | 2026-02-15 | 2026-01-22 | 2026-01-27 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-011 | TRG-012 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process be fulfilled to be supplied of the active substance or change in the manufacturer (including where relevant quality control testing sites) of the active substance, where no Ph. Eur. Certificate of Suitability is part of the approved dossier - b) Introduction of a manufacturer of the active substance supported by an ASMF | Novalex | CMC/Quality | II |  | Archived | High | High | 2025-03-31 | 2025-04-20 | 2025-08-01 | 2025-09-10 | 2025-12-01 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-012 | TRG-013 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process be fulfilled to be supplied of the active substance or change in the manufacturer (including where relevant quality control testing sites) of the active substance, where no Ph. Eur. Certificate of Suitability is part of the approved dossier - c) The proposed manufacturer uses a substantially different route of synthesis or manufacturi | Novalex | CMC/Quality | II |  | Archived | High | High | 2025-04-30 | 2025-05-16 | 2025-09-04 | 2025-10-24 | 2025-12-01 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-013 | TRG-014 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process be fulfilled to be supplied of the active substance or change in the manufacturer (including where relevant quality control testing sites) of the active substance, where no Ph. Eur. Certificate of Suitability is part of the approved dossier - d) New manufacturer of material for which an assessment is required of viral safety and/or TS | Novalex | CMC/Quality | II |  | Archived | High | High | 2025-05-30 | 2025-06-08 | 2025-09-25 | 2025-11-09 | 2026-01-23 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-014 | TRG-016 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process be fulfilled to be supplied of the active substance or change in the manufacturer (including where relevant quality control testing sites) of the active substance, where no Ph. Eur. Certificate of Suitability is part of the approved dossier - f) Changes to quality control testing arrangements for the active substance-replace | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-08-20 | 2024-08-24 | 2024-09-23 | 2025-02-15 | 2025-03-16 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-015 | TRG-017 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process be fulfilled to be supplied of the active substance or change in the manufacturer (including where relevant quality control testing sites) of the active substance, where no Ph. Eur. Certificate of Suitability is part of the approved dossier - g) Introduction of a new manufacturer of the active substance that is not supported by an ASM | Novalex | CMC/Quality | II |  | Archived | High | High | 2025-06-29 | 2025-07-26 | 2025-09-28 | 2025-12-05 | 2026-02-03 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-016 | TRG-018 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process be fulfilled to be supplied of the active substance or change in the manufacturer (including where relevant quality control testing sites) of the active substance, where no Ph. Eur. Certificate of Suitability is part of the approved dossier - h) Addition of an alternative sterilisation site for the active substance using | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2024-12-06 | 2024-12-10 | 2025-01-16 | 2025-02-03 | 2025-03-20 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-017 | TRG-019 | Change in the manufacturer of a starting material/ reagent/intermediate used in the manufacturing process of the active substance or change in the manufacturer | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-08-30 | 2024-09-01 | 2024-10-01 | 2025-02-12 | 2025-03-12 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-018 | TRG-022 | Changes in the manufacturing process of the active substance - a) Minor change in the manufacturing process of the 1, 2, 3, 4, 5, 6, 1, 2, 3 active substanc | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-09-09 | 2024-09-16 | 2024-10-16 | 2024-12-21 | 2024-12-25 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-019 | TRG-023 | Changes in the manufacturing process of the active substance be fulfilled to be supplied - b) Substantial change to the manufacturing process of the active substance which may have a s | Novalex | CMC/Quality | II |  | Archived | High | High | 2025-07-29 | 2025-08-25 | 2025-12-17 | 2026-02-11 | 2026-03-24 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-020 | TRG-026 | Changes in the manufacturing process of the active substance be fulfilled to be supplied - e) Minor change to the restricted part of an Active Substance Master File | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2024-12-27 | 2024-12-27 | 2025-02-02 | 2025-02-06 | 2025-02-26 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-021 | TRG-027 | Change in batch size (including batch size ranges) of active substance or intermediate used in the manufac turing process of the active substance - a) Up to 10 | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-09-19 | 2024-09-24 | 2024-10-24 | 2025-01-31 | 2025-02-20 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-022 | TRG-028 | Change in batch size (including batch size ranges) of active substance or intermediate used in the manufac turing process of the active substance - b) Downscali | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-09-29 | 2024-10-05 | 2024-11-04 | 2024-11-15 | 2024-12-14 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-023 | TRG-030 | Change in batch size (including batch size ranges) of active substance or intermediate used in the manufac be fulfilled to be supplied turing process of the active substance - d) More than 10-fold increase compared to the originally approved batch size | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-01-17 | 2025-01-17 | 2025-02-23 | 2025-03-16 | 2025-04-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-024 | TRG-032 | Change to in-process tests or limits applied during the manufacture of the active substance - a) Tightening of in-process limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-10-09 | 2024-10-09 | 2024-11-08 | 2025-04-03 | 2025-04-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-025 | TRG-033 | Change to in-process tests or limits applied during the manufacture of the active substance - b) Addition of a new in-process test and limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-10-19 | 2024-10-24 | 2024-11-23 | 2025-03-17 | 2025-03-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-026 | TRG-034 | Change to in-process tests or limits applied during the manufacture of the active substance - c) Deletion of a non-significant in-process test | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-10-29 | 2024-10-29 | 2024-11-28 | 2025-01-02 | 2025-01-22 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-027 | TRG-035 | Change to in-process tests or limits applied during the manufacture of the active substance be fulfilled to be supplied - d) Widening of the approved in-process test limits, which may have a significant effect on th | Novalex | CMC/Quality | II |  | Archived | High | High | 2025-08-28 | 2025-09-27 | 2026-01-03 | 2026-02-12 | 2026-03-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-028 | TRG-036 | Change to in-process tests or limits applied during the manufacture of the active substance be fulfilled to be supplied - e) Deletion of an in-process test which may have a significant effect on the overall quality | Novalex | CMC/Quality | II |  | Implementation Overdue | High | High | 2025-09-27 | 2025-10-17 | 2026-01-30 | 2026-04-17 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-029 | TRG-037 | Change to in-process tests or limits applied during the manufacture of the active substance be fulfilled to be supplied - f) Addition or replacement of an in-process test as a result of a safety or quality | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-02-07 | 2025-02-15 | 2025-03-24 | 2025-03-25 | 2025-04-20 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-030 | TRG-039 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - a) Tightening of specification limits for medicinal products subject to Offic | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-08-10 | 2024-08-11 | 2024-09-10 | 2024-08-14 | 2024-08-15 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-031 | TRG-040 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - b) Tightening of specification limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-11-08 | 2024-11-10 | 2024-12-10 | 2025-03-17 | 2025-04-10 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-032 | TRG-041 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - c) Addition of a new specification parameter to the specification | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-11-18 | 2024-11-20 | 2024-12-20 | 2025-02-28 | 2025-03-15 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-033 | TRG-042 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - d) Deletion of a non-significant specification parameter (e.g. deletion of an | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-11-28 | 2024-11-29 | 2024-12-29 | 2025-02-23 | 2025-03-09 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-034 | TRG-043 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - e) Deletion of a specification parameter which may have a significant effect on the overall q | Novalex | CMC/Quality | II |  | Implementation Overdue | High | High | 2025-10-27 | 2025-11-04 | 2026-02-19 | 2026-04-03 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-035 | TRG-044 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - f) Change outside the approved specifications limits range for the active substance | Novalex | CMC/Quality | II |  | Approved - Pending Implementation | High | High | 2025-11-26 | 2025-12-19 | 2026-03-24 | 2026-06-07 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-036 | TRG-045 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - g) Widening of the approved specifications limits for starting materials/intermediates, which | Novalex | CMC/Quality | II |  | Implementation Overdue | High | High | 2025-12-26 | 2026-01-17 | 2026-03-19 | 2026-04-29 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-037 | TRG-047 | Change in the specification parameters and/or limits of an active substance, starting material/intermedi be fulfilled to be supplied ate/reagent used in the manufacturing process of the active substance - i) Where there is no monograph in the European Pharmacopoeia or the national | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-02-28 | 2025-03-05 | 2025-04-11 | 2025-05-11 | 2025-06-22 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-038 | TRG-048 | Change in test procedure for active substance or starting material/reagent/intermediate used in the manufacturing process of the active substance - a) Minor cha | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-12-08 | 2024-12-14 | 2025-01-13 | 2025-02-13 | 2025-02-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-039 | TRG-049 | Change in test procedure for active substance or starting material/reagent/intermediate used in the manufacturing process of the active substance - b) Deletion | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-12-18 | 2024-12-18 | 2025-01-17 | 2025-01-21 | 2025-02-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-040 | TRG-050 | Change in test procedure for active substance or starting material/reagent/intermediate used in the manufacturing process of the active substance - c) Other cha | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2024-12-28 | 2024-12-28 | 2025-01-27 | 2025-03-04 | 2025-03-06 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-041 | TRG-052 | Change in test procedure for active substance or starting material/reagent/intermediate used in the manu be fulfilled to be supplied facturing process of the active substance - e) Other changes to a test procedure (including replacement or addition) for the active | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-03-21 | 2025-03-27 | 2025-05-03 | 2025-05-07 | 2025-06-16 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-042 | TRG-053 | Change in immediate packaging of the active substance - a) Qualitative and/or quantitative composition | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-01-07 | 2025-01-08 | 2025-02-07 | 2025-06-19 | 2025-07-18 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-043 | TRG-055 | Change in immediate packaging of the active substance be fulfilled to be supplied - c) Liquid active substances (non-sterile) | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-04-11 | 2025-04-19 | 2025-05-26 | 2025-06-10 | 2025-07-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-044 | TRG-056 | Change in the specification parameters and/or limits of the immediate packaging of the active substance - a) Tightening of specification limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-01-17 | 2025-01-21 | 2025-02-20 | 2025-04-01 | 2025-04-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-045 | TRG-057 | Change in the specification parameters and/or limits of the immediate packaging of the active substance - b) Addition of a new specification parameter to the 1, | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-01-27 | 2025-02-01 | 2025-03-03 | 2025-03-21 | 2025-03-30 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-046 | TRG-058 | Change in the specification parameters and/or limits of the immediate packaging of the active substance - c) Deletion of a non-significant specification 1, 2 1, | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-02-06 | 2025-02-07 | 2025-03-09 | 2025-04-11 | 2025-05-07 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-047 | TRG-059 | Change in the specification parameters and/or limits of the immediate packaging of the active substance be fulfilled to be supplied - d) Addition or replacement of a specification parameter as a result of a safety | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-05-02 | 2025-05-03 | 2025-06-09 | 2025-07-07 | 2025-07-20 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-048 | TRG-060 | Change in test procedure for the immediate packaging of the active substance - a) Minor changes to an approved test procedure | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-02-16 | 2025-02-16 | 2025-03-18 | 2025-03-24 | 2025-04-22 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-049 | TRG-061 | Change in test procedure for the immediate packaging of the active substance - b) Other changes to a test procedure (including 1, 3, 4 1, 2 replacement or addit | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-02-26 | 2025-03-01 | 2025-03-31 | 2025-04-04 | 2025-04-25 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-050 | TRG-062 | Change in test procedure for the immediate packaging of the active substance - c) Deletion of a test procedure if an alternative test 5 1 procedure is already a | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-03-08 | 2025-03-14 | 2025-04-13 | 2025-05-28 | 2025-06-23 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-051 | TRG-065 | Change in the retest period/storage period or storage conditions of the active substance where no Ph. Eur. Certificate of Suitability covering the retest period | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-03-18 | 2025-03-24 | 2025-04-23 | 2025-08-02 | 2025-08-13 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-052 | TRG-066 | Introduction of a new design space or extension of an approved design space for the active substance, be fulfilled to be supplied concerning: - a) One unit operation in the manufacturing process of 1, 2, 3 the active substance including | Novalex | CMC/Quality | II |  | Approved - Pending Implementation | High | High | 2026-01-25 | 2026-02-24 | 2026-04-27 | 2026-06-30 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-053 | TRG-067 | Introduction of a new design space or extension of an approved design space for the active substance, be fulfilled to be supplied concerning: - b) Test procedures for starting materials/reagents/in 1, 2, 3 termediates and/or the active s | Novalex | CMC/Quality | II |  | Under Assessment | High | High | 2026-02-24 | 2026-03-06 |  | 2026-07-07 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-054 | TRG-068 | Introduction of a post approval change management protocol related to the active substance be fulfilled to be supplied | Novalex | CMC/Quality | II |  | Under Assessment | High | High | 2026-03-26 | 2026-04-24 |  | 2026-09-25 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-055 | TRG-069 | Deletion of an approved change management protocol related to the active substance | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-08-24 | 2024-08-27 | 2024-09-26 | 2024-08-31 | 2024-09-05 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-056 | TRG-070 | Changes to an approved change management protocol be fulfilled to be supplied - a) Major changes to an approved change management protocol | Novalex | CMC/Quality | II |  | Under Assessment | High | High | 2026-04-25 | 2026-05-05 |  | 2026-09-19 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-057 | TRG-072 | Implementation of changes foreseen in an approved change management protocol be fulfilled to be supplied - a) The implementation of the change requires no further supportive data | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-09-07 | 2024-09-10 | 2024-10-10 | 2024-09-16 | 2024-09-23 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-058 | TRG-073 | Implementation of changes foreseen in an approved change management protocol be fulfilled to be supplied - b) The implementation of the change requires further supportive data | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-05-23 | 2025-06-03 | 2025-07-10 | 2025-07-15 | 2025-08-20 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-059 | TRG-075 | Change or addition of imprints, bossing or other markings including replacement, or addition of inks used for product marking. - a) Changes in imprints, bossing | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-09-21 | 2024-09-23 | 2024-10-23 | 2024-09-28 | 2024-09-29 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-060 | TRG-076 | Change or addition of imprints, bossing or other markings including replacement, or addition of inks used be fulfilled to be supplied for product marking. - b) Changes in scoring/break lines intended to divide into equal doses | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-06-13 | 2025-06-26 | 2025-08-02 | 2025-08-29 | 2025-09-21 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-061 | TRG-077 | Change in the shape or dimensions of the phar maceutical form - a) Immediate release tablets, capsules, suppositories 1, 2, 3, 4 1, 4 and pessaries | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-10-05 | 2024-10-05 | 2024-11-04 | 2024-10-12 | 2024-10-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-062 | TRG-078 | Change in the shape or dimensions of the phar maceutical form be fulfilled to be supplied - b) Gastro-resistant, modified or prolonged release pharmaceutical forms and sco | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-07-04 | 2025-07-13 | 2025-08-19 | 2025-08-25 | 2025-10-05 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-063 | TRG-079 | Change in the shape or dimensions of the phar maceutical form - c) Addition of a new kit for a radiopharmaceutical preparation with another fill volume | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-05-25 |  |  | 2026-10-07 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-064 | TRG-082 | Change in coating weight of oral dosage forms or change in weight of capsule shells - a) Solid oral pharmaceutical forms | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-03-28 | 2025-04-03 | 2025-05-03 | 2025-05-06 | 2025-05-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-065 | TRG-083 | Change in coating weight of oral dosage forms or change in weight of capsule shells - b) Gastro-resistant, modified or prolonged release pharmaceutical forms wh | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-06-24 |  |  | 2026-12-18 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-066 | TRG-084 | Change in concentration of a single-dose, total use parenteral product, where the amount of active substance per unit dose (i.e. the strength) remains the same | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-07-24 |  |  | 2027-03-02 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-067 | TRG-085 | Deletion of the solvent/diluent container from the pack | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-08-23 |  |  | 2026-12-13 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-068 | TRG-086 | Replacement or addition of a manufacturing site for part or all of the manufacturing process of the finished product - a) Secondary packaging site | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-10-19 | 2024-10-21 | 2024-11-20 | 2024-10-25 | 2024-10-31 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-069 | TRG-087 | Replacement or addition of a manufacturing site for part or all of the manufacturing process of the finished product - b) Primary packaging site | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-11-02 | 2024-11-03 | 2024-12-03 | 2024-11-07 | 2024-11-13 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-070 | TRG-089 | Replacement or addition of a manufacturing site for part or all of the manufacturing process of the finished product - d) Site which requires an initial or prod | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-09-22 |  |  | 2027-03-19 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-071 | TRG-090 | Replacement or addition of a manufacturing site for part or all of the manufacturing process of the be fulfilled to be supplied finished product - e) Site where any manufacturing operation(s) take place, except batch-release | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-07-25 | 2025-07-25 | 2025-08-31 | 2025-09-15 | 2025-10-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-072 | TRG-092 | Change to importer, batch release arrangements and quality control testing of the finished product - a) Replacement or addition of a site where batch 2, 3, 4, 5 | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-04-07 | 2025-04-07 | 2025-05-07 | 2025-08-22 | 2025-09-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-073 | TRG-095 | Change in the manufacturing process of the finished product, including an intermediate used in the manufacture of the finished product - a) Minor change in the | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-04-17 | 2025-04-23 | 2025-05-23 | 2025-07-21 | 2025-08-15 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-074 | TRG-096 | Change in the manufacturing process of the finished product, including an intermediate used in the manufacture of the finished product - b) Substantial changes | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-10-22 |  |  | 2027-03-13 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-075 | TRG-098 | Change in the manufacturing process of the finished product, including an intermediate used in the manufacture of the finished product - d) Introduction of a no | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-11-21 |  |  | 2027-03-29 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-076 | TRG-099 | Change in the manufacturing process of the finished product, including an intermediate used in the manufacture of the finished product - e) Introduction or incr | Novalex | CMC/Quality | II |  | Not Started | High | High | 2026-12-21 |  |  | 2027-06-06 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-077 | TRG-100 | Change in the manufacturing process of the finished product, including an intermediate used in the be fulfilled to be supplied manufacture of the finished product - f) Minor change in the manufacturing process of an aqueous oral suspension | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-08-15 | 2025-08-23 | 2025-09-29 | 2025-10-25 | 2025-11-01 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-078 | TRG-101 | Change in the batch size (including batch size ranges) of the finished product - a) Up to 10-fold compared to the originally approved 1, 2, 3, 4, 5, 7 1, 4 batc | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-04-27 | 2025-05-04 | 2025-06-03 | 2025-07-08 | 2025-07-16 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-079 | TRG-102 | Change in the batch size (including batch size ranges) of the finished product - b) Downscaling down to 10-fold | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-05-07 | 2025-05-10 | 2025-06-09 | 2025-08-11 | 2025-08-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-080 | TRG-104 | Change in the batch size (including batch size ranges) of the finished product - d) The change relates to all other pharmaceutical forms manufactured by complex | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-01-20 |  |  | 2027-05-18 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-081 | TRG-105 | Change in the batch size (including batch size ranges) of the finished product be fulfilled to be supplied - e) More than 10-fold increase compared to the originally approved batch size | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-09-05 | 2025-09-12 | 2025-10-19 | 2025-11-14 | 2025-12-14 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-082 | TRG-107 | Change to in-process tests or limits applied during the manufacture of the finished product - a) Tightening of in-process limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-05-17 | 2025-05-17 | 2025-06-16 | 2025-09-06 | 2025-09-25 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-083 | TRG-108 | Change to in-process tests or limits applied during the manufacture of the finished product - b) Addition of a new test(s) and limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-05-27 | 2025-05-28 | 2025-06-27 | 2025-11-13 | 2025-11-18 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-084 | TRG-109 | Change to in-process tests or limits applied during the manufacture of the finished product - c) Deletion of a non-significant in-process test | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-06-06 | 2025-06-13 | 2025-07-13 | 2025-09-02 | 2025-09-11 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-085 | TRG-110 | Change to in-process tests or limits applied during the manufacture of the finished product - d) Deletion of an in-process test which may have a significant eff | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-02-19 |  |  | 2027-08-24 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-086 | TRG-111 | Change to in-process tests or limits applied during the manufacture of the finished product - e) Widening of the approved IPC limits, which may have a significa | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-03-21 |  |  | 2027-08-18 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-087 | TRG-112 | Change to in-process tests or limits applied during the manufacture of the finished product be fulfilled to be supplied - f) Addition or replacement of an in-process test as a result of a safety or | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-09-26 | 2025-10-04 | 2025-11-10 | 2025-11-26 | 2025-12-21 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-088 | TRG-113 | Change in the specification parameters and/or limits of an excipient - a) Tightening of specification limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-06-16 | 2025-06-21 | 2025-07-21 | 2025-08-01 | 2025-08-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-089 | TRG-114 | Change in the specification parameters and/or limits of an excipient - b) Addition of a new specification parameter to the 1, 2, 5, 6, 7 1, 2, 3, 4, 6, 8 specif | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-06-26 | 2025-06-30 | 2025-07-30 | 2025-09-20 | 2025-09-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-090 | TRG-115 | Change in the specification parameters and/or limits of an excipient - c) Deletion of a non-significant specification 1, 2, 8 1, 2, 7 parameter (e.g. deletion o | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-07-06 | 2025-07-09 | 2025-08-08 | 2025-11-26 | 2025-12-18 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-091 | TRG-116 | Change in the specification parameters and/or limits of an excipient - d) Change outside the approved specifications limits range | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-04-20 |  |  | 2027-10-12 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-092 | TRG-117 | Change in the specification parameters and/or limits of an excipient - e) Deletion of a specification parameter which may have a significant effect on the overa | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-05-20 |  |  | 2027-11-12 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-093 | TRG-119 | Change in the specification parameters and/or limits of an excipient be fulfilled to be supplied - g) Where there is no monograph in the European Pharmacopoeia or the natio | Novalex | CMC/Quality | IB |  | Implementation Overdue | Medium | Medium | 2025-10-17 | 2025-10-22 | 2025-11-28 | 2025-12-13 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-094 | TRG-120 | Change in test procedure for an excipient - a) Minor changes to an approved test procedure | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-07-16 | 2025-07-16 | 2025-08-15 | 2025-09-25 | 2025-10-03 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-095 | TRG-121 | Change in test procedure for an excipient - b) Deletion of a test procedure if an alternative test 5 1 procedure is already authorised | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-07-26 | 2025-08-01 | 2025-08-31 | 2025-12-24 | 2026-01-15 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-096 | TRG-123 | Change in test procedure for an excipient be fulfilled to be supplied - d) Other changes to a test procedure (including replacement or addition) | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-11-07 | 2025-11-13 | 2025-12-20 | 2025-12-30 | 2026-01-14 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-097 | TRG-125 | Change in source of an excipient or reagent with TSE risk - b) Change or introduction of a TSE risk material or replacement of a TSE risk material from a | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-06-19 |  |  | 2027-11-06 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-098 | TRG-126 | Change in synthesis or recovery of a non-phar macopoeial excipient (when described in the dossier) or a novel excipient - a) Minor change in synthesis or recove | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-08-05 | 2025-08-09 | 2025-09-08 | 2025-09-16 | 2025-10-16 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-099 | TRG-127 | Change in synthesis or recovery of a non-phar macopoeial excipient (when described in the dossier) or a novel excipient - b) The specifications are affected or | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-07-19 |  |  | 2027-12-26 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-100 | TRG-129 | Change in the specification parameters and/or limits of the finished product - a) Tightening of specification limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-08-15 | 2025-08-15 | 2025-09-14 | 2025-10-12 | 2025-11-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-101 | TRG-130 | Change in the specification parameters and/or limits of the finished product - b) Tightening of specification limits for medicinal 1, 2, 3, 4 1, 2 products subj | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-11-16 | 2024-11-18 | 2024-12-18 | 2024-11-23 | 2024-11-25 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-102 | TRG-131 | Change in the specification parameters and/or limits of the finished product - c) Addition of a new specification parameter to the 1, 2, 5, 6, 7 1, 2, 3, 4, 5, | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-08-25 | 2025-08-30 | 2025-09-29 | 2025-10-28 | 2025-11-08 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-103 | TRG-132 | Change in the specification parameters and/or limits of the finished product - d) Deletion of a non-significant specification 1, 2, 9 1, 2, 6 parameter (e.g. de | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-09-04 | 2025-09-11 | 2025-10-11 | 2025-10-20 | 2025-11-01 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-104 | TRG-133 | Change in the specification parameters and/or limits of the finished product - e) Change outside the approved specifications limits range | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-08-18 |  |  | 2028-03-03 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-105 | TRG-134 | Change in the specification parameters and/or limits of the finished product - f) Deletion of a specification parameter which may have a significant effect on t | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-09-17 |  |  | 2028-03-05 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-106 | TRG-136 | Change in the specification parameters and/or limits of the finished product - h) Update of the dossier to comply with the 1, 2, 3, 4, 7, 8 1, 2 provisions of a | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-11-30 | 2024-12-03 | 2025-01-02 | 2024-12-03 | 2024-12-07 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-107 | TRG-137 | Change in the specification parameters and/or limits of the finished product - i) Ph. Eur. 2.9.40 Uniformity of dosage units is 1, 2,10 1, 2, 4 introduced to re | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-09-14 | 2025-09-16 | 2025-10-16 | 2025-11-29 | 2025-12-04 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-108 | TRG-138 | Change in test procedure for the finished product - a) Minor changes to an approved test procedure | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-09-24 | 2025-09-27 | 2025-10-27 | 2025-11-07 | 2025-12-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-109 | TRG-139 | Change in test procedure for the finished product - b) Deletion of a test procedure if an alternative 4 1 method is already authorised | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-10-04 | 2025-10-06 | 2025-11-05 | 2026-02-13 | 2026-02-13 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-110 | TRG-141 | Change in test procedure for the finished product be fulfilled to be supplied - d) Other changes to a test procedure (including replacement or addition) | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-11-28 | 2025-12-09 | 2026-01-15 | 2026-02-06 | 2026-03-17 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-111 | TRG-142 | Change in test procedure for the finished product - e) Update of the test procedure to comply with the 2, 3, 4, 5 1 updated general monograph in | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-10-14 | 2025-10-14 | 2025-11-13 | 2026-02-23 | 2026-03-08 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-112 | TRG-143 | Change in test procedure for the finished product - f) To reflect compliance with the Ph.Eur. and remove 2, 3, 4, 5 1 reference to the outdated i | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-10-24 | 2025-10-27 | 2025-11-26 | 2025-11-24 | 2025-12-05 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-113 | TRG-144 | Variations related to the introduction of real-time release or parametric release in the manufacture of the finished product | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-10-17 |  |  | 2028-03-02 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-114 | TRG-147 | Change in the specification parameters and/or limits of the immediate packaging of the finished product - a) Tightening of specification limits | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-11-03 | 2025-11-06 | 2025-12-06 | 2026-03-10 | 2026-03-10 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-115 | TRG-148 | Change in the specification parameters and/or limits of the immediate packaging of the finished product - b) Addition of a new specification parameter to the 1, | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-11-13 | 2025-11-16 | 2025-12-16 | 2026-01-08 | 2026-01-08 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-116 | TRG-149 | Change in the specification parameters and/or limits of the immediate packaging of the finished product - c) Deletion of a non-significant specification 1, 2 1, | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-11-23 | 2025-11-25 | 2025-12-25 | 2026-01-04 | 2026-01-13 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-117 | TRG-150 | Change in the specification parameters and/or limits of the immediate packaging of the finished product be fulfilled to be supplied - d) Addition or replacement of a specification parameter as a result of a safety | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2025-12-19 | 2025-12-28 | 2026-02-03 | 2026-02-14 | 2026-03-26 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-118 | TRG-151 | Change in test procedure for the immediate packaging of the finished product - a) Minor changes to an approved test procedure | Novalex | CMC/Quality | IA |  | Implemented | Low | Low | 2025-12-03 | 2025-12-08 | 2026-01-07 | 2026-04-19 | 2026-04-29 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-119 | TRG-152 | Change in test procedure for the immediate packaging of the finished product - b) Other changes to a test procedure (including 1, 3, 4 1, 2 replacement or addit | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-12-13 | 2025-12-14 | 2026-01-13 | 2026-03-21 | 2026-04-08 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-120 | TRG-153 | Change in test procedure for the immediate packaging of the finished product - c) Deletion of a test procedure if an alternative test 5 1 procedure is already a | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2025-12-23 | 2025-12-28 | 2026-01-27 | 2026-03-09 | 2026-04-04 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-121 | TRG-154 | Change in shape or dimensions of the container or closure (immediate packaging) - a) Non-sterile medicinal products | Novalex | CMC/Quality | IA |  | Implemented | Low | Low | 2026-01-02 | 2026-01-05 | 2026-02-04 | 2026-05-02 | 2026-05-08 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-122 | TRG-155 | Change in shape or dimensions of the container or closure (immediate packaging) - b) The change in shape or dimensions concerns a fundamental part of the packag | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-11-16 |  |  | 2028-04-19 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-123 | TRG-156 | Change in shape or dimensions of the container or closure (immediate packaging) be fulfilled to be supplied - c) Sterile medicinal products | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2026-01-09 | 2026-01-13 | 2026-02-19 | 2026-03-11 | 2026-03-19 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-124 | TRG-157 | Change in pack size of the finished product be fulfilled to be supplied - a) Change in the number of units (e.g. tablets, ampoules, etc.) in a pack . Change within th | Novalex | CMC/Quality | IB |  | Implemented | Medium | Medium | 2026-01-30 | 2026-02-11 | 2026-03-20 | 2026-03-28 | 2026-04-26 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-125 | TRG-158 | Change in pack size of the finished product - b) Deletion of pack size(s) | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2026-01-12 | 2026-01-13 | 2026-02-12 | 2026-03-06 | 2026-03-25 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-126 | TRG-160 | Change in pack size of the finished product be fulfilled to be supplied - d) Change in the fill weight/fill volume of non- parenteral multi-dose (or single-dose) | Novalex | CMC/Quality | IB |  | Implemented | Medium | Medium | 2026-02-20 | 2026-02-21 | 2026-03-30 | 2026-04-03 | 2026-04-22 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-127 | TRG-161 | Change in any part of the (primary) packaging material not in contact with the finished product formu be fulfilled to be supplied lation (such as colour of flip-off caps, colour code rings on ampoules, change of needle shield (different plastic used)) - a) Change that affects the product information | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-12-14 | 2024-12-17 | 2025-01-16 | 2024-12-22 | 2024-12-28 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-128 | TRG-162 | Change in any part of the (primary) packaging material not in contact with the finished product formu be fulfilled to be supplied lation (such as colour of flip-off caps, colour code rings on ampoules, change of needle shield (different plastic used)) - b) Change that does not affect the product information | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2026-01-22 | 2026-01-24 | 2026-02-23 | 2026-02-28 | 2026-03-17 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-129 | TRG-163 | Change in supplier of packaging components or devices (when mentioned in the dossier) - a) Deletion of a supplier | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2026-02-01 | 2026-02-04 | 2026-03-06 | 2026-03-14 | 2026-03-22 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-130 | TRG-164 | Change in supplier of packaging components or devices (when mentioned in the dossier) - b) Replacement or addition of a supplier | Novalex | CMC/Quality | IA |  | Archived | Low | Low | 2026-02-11 | 2026-02-14 | 2026-03-16 | 2026-03-19 | 2026-04-02 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-131 | TRG-165 | Change in supplier of packaging components or devices (when mentioned in the dossier) - c) Any change to suppliers of spacer devices for metered dose inhalers | Novalex | CMC/Quality | II |  | Not Started | High | High | 2027-12-16 |  |  | 2028-05-25 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-132 | TRG-166 | Change in the shelf-life or storage conditions of the finished product - a) Reduction of the shelf life of the finished product 1. As packaged for sale 1 1, 2, | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-11-15 | 2024-11-18 | 2024-12-18 | 2024-11-24 | 2024-12-01 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-133 | TRG-169 | Change in the shelf-life or storage conditions of the finished product be fulfilled to be supplied - d) Change in storage conditions of the finished product or the diluted/reconstituted | Novalex | CMC/Quality | IB |  | Approved - Pending Implementation | Medium | Medium | 2026-03-13 | 2026-03-25 | 2026-05-01 | 2026-05-19 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-134 | TRG-170 | Change in the shelf-life or storage conditions of the finished product - e) Change to an approved stability protocol | Novalex | CMC/Quality | IA |  | Implemented | Low | Low | 2026-02-21 | 2026-02-23 | 2026-03-25 | 2026-05-03 | 2026-05-03 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-135 | TRG-171 | Introduction of a new design space or extension of an approved design space for the finished product, concerning: - a) One or more unit operations in the manufa | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-01-15 |  |  | 2028-07-10 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-136 | TRG-172 | Introduction of a new design space or extension of an approved design space for the finished product, concerning: - b) Test procedures for excipients/intermedia | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-02-14 |  |  | 2028-08-24 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-137 | TRG-173 | Introduction of a post approval change management protocol related to the finished product | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-03-15 |  |  | 2028-10-01 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-138 | TRG-174 | Deletion of an approved change management protocol related to the finished product | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2024-12-28 | 2024-12-28 | 2025-01-27 | 2025-01-04 | 2025-01-10 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-139 | TRG-175 | Changes to an approved change management protocol - a) Major changes to an approved change management protocol | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-04-14 |  |  | 2028-10-06 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-140 | TRG-177 | Implementation of changes foreseen in an approved change management protocol - a) The implementation of the change requires no 1 1, 2, 4 further supportive data | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2025-01-11 | 2025-01-12 | 2025-02-11 | 2025-01-19 | 2025-01-21 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-141 | TRG-073 | Implementation of changes foreseen in an approved change management protocol - b) The implementation of the change requires further supportive data | Novalex | CMC/Quality | IB |  | Under Assessment | Medium | Medium | 2026-04-03 | 2026-04-12 |  | 2026-05-22 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-142 | TRG-180 | Update to the â€˜Adventitious Agents Safety Evalu ationâ€™ information (section 3.2.A.2) - a) Studies related to manufacturing steps investigated for the first time | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-05-14 |  |  | 2028-10-29 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-143 | TRG-181 | Update to the ‘Adventitious Agents Safety Evaluation’ information (section 3.2.A.2) be fulfilled to be supplied - b) Replacement of obsolete studies related to manu facturing steps and adventitious agents al | Novalex | CMC/Quality | IB |  | Under Assessment | Medium | Medium | 2026-04-24 | 2026-04-24 |  | 2026-06-08 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-144 | TRG-182 | Submission of a new or updated Ph. Eur. certificate of suitability or deletion of Ph. Eur. certificate be fulfilled to be supplied of suitability: - a) European Pharmacopoeial Certificate of Suitability to the relevant Ph. Eur. Monograph. 1. | Novalex | CMC/Quality | IB |  | Archived | Medium | Medium | 2026-01-15 | 2026-01-16 | 2026-02-22 | 2026-02-27 | 2026-03-01 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-145 | TRG-183 | Submission of a new or updated Ph. Eur. certificate of suitability or deletion of Ph. Eur. certificate of suitability: - b) European Pharmacopoeial TSE Certific | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-06-13 |  |  | 2029-01-07 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-146 | TRG-184 | Change to comply with Ph. Eur. or with a national pharmacopoeia of a Member State - a) Change of specification(s) of a former non-EU Phar macopoeial substance t | Novalex | CMC/Quality | IA |  | Approved - Pending Implementation | Low | Low | 2026-03-03 | 2026-03-09 | 2026-04-08 | 2026-08-25 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-147 | TRG-185 | Change to comply with Ph. Eur. or with a national pharmacopoeia of a Member State - b) Change to comply with an update of the relevant 1, 2, 4, 5 1, 2, 3, 4 mon | Novalex | CMC/Quality | IA |  | Approved - Pending Implementation | Low | Low | 2026-03-13 | 2026-03-19 | 2026-04-18 | 2026-05-27 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-148 | TRG-186 | Change to comply with Ph. Eur. or with a national pharmacopoeia of a Member State - c) Change in specifications from a national phar 1, 4, 5 1, 2, 3, 4 macopoei | Novalex | CMC/Quality | IA |  | Approved - Pending Implementation | Low | Low | 2026-03-23 | 2026-03-26 | 2026-04-25 | 2026-08-02 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-149 | TRG-187 | Change of a measuring or administration device - a) Addition or replacement of a device which is not an integrated part of the primary packagi | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-07-13 |  |  | 2028-11-15 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-150 | TRG-188 | Change of a measuring or administration device - b) Deletion of a device | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2025-01-25 | 2025-01-26 | 2025-02-25 | 2025-01-29 | 2025-02-05 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-151 | TRG-189 | Change of a measuring or administration device - c) Addition or replacement of a device which is an integrated part of the primary packaging | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-08-12 |  |  | 2029-03-06 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-152 | TRG-190 | Change in specification parameters and/or limits of a measuring or administration device for veterinary medicinal products - a) Tightening of specification limi | Novalex | CMC/Quality | IA |  | Approved - Pending Implementation | Low | Low | 2026-04-02 | 2026-04-05 | 2026-05-05 | 2026-07-15 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-153 | TRG-191 | Change in specification parameters and/or limits of a measuring or administration device for veterinary medicinal products - b) Addition of a new specification | Novalex | CMC/Quality | IA |  | Approved - Pending Implementation | Low | Low | 2026-04-12 | 2026-04-13 | 2026-05-13 | 2026-06-20 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-154 | TRG-192 | Change in specification parameters and/or limits of a measuring or administration device for veterinary medicinal products - c) Widening of the approved specifi | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-09-11 |  |  | 2029-03-11 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-155 | TRG-193 | Change in specification parameters and/or limits of a measuring or administration device for veterinary medicinal products - d) Deletion of a specification para | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-10-11 |  |  | 2029-02-11 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-156 | TRG-194 | Change in specification parameters and/or limits of a measuring or administration device for veterinary medicinal products - e) Addition of a specification para | Novalex | CMC/Quality | IB |  | Not Started | Medium | Medium | 2026-05-15 |  |  | 2026-07-28 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-157 | TRG-195 | Change in specification parameters and/or limits of a measuring or administration device for veterinary medicinal products - f) Deletion of a non-significant sp | Novalex | CMC/Quality | IA |  | Under Assessment | Low | Low | 2026-04-22 | 2026-04-26 |  | 2026-08-30 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-158 | TRG-196 | Change in test procedure of a measuring or admin istration device for veterinary medicinal products - a) Minor change to an approved test procedure | Novalex | CMC/Quality | IA |  | Under Assessment | Low | Low | 2026-05-02 | 2026-05-03 |  | 2026-07-30 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-159 | TRG-197 | Change in test procedure of a measuring or admin istration device for veterinary medicinal products - b) Other changes to a test procedure (including 1, 3 1, 2 | Novalex | CMC/Quality | IA |  | In Preparation | Low | Low | 2026-05-12 |  |  | 2026-07-01 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-160 | TRG-198 | Change in test procedure of a measuring or admin istration device for veterinary medicinal products - c) Deletion of a test procedure if an alternative test 4 1 | Novalex | CMC/Quality | IA |  | Not Started | Low | Low | 2026-05-22 |  |  | 2026-08-30 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-161 | TRG-206 | Update of the quality dossier intended to implement the outcome of a Union referral procedure - a) The change implements the outcome of the referral | Novalex | CMC/Quality | IAIN |  | Archived | Medium | Low/Medium | 2025-02-08 | 2025-02-11 | 2025-03-13 | 2025-02-15 | 2025-02-18 | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-162 | TRG-207 | Update of the quality dossier intended to implement the outcome of a Union referral procedure - b) The harmonisation of the quality dossier was not part of the | Novalex | CMC/Quality | II |  | Not Started | High | High | 2028-11-10 |  |  | 2029-06-11 |  | CMC Regulatory Affairs Lead with Quality/Manufacturing/QA | No
NVX-SUB-163 | TRG-208 | Change(s) in the Summary of Product Character istics, Labelling or Package Leaflet intended to be fulfilled to be supplied implement the outcome of a Union referral procedure - a) The medicinal product is covered by the defined 1 1, 2, 3 scope of the procedure | Novalex | Clinical/Safety Labelling | IAIN | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | High | Low/Medium | 2025-06-15 | 2025-06-15 | 2025-07-15 | 2025-06-19 | 2025-06-26 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-164 | TRG-209 | Change(s) in the Summary of Product Characteristics, Labelling or Package Leaflet intended to implement the outcome of a Union referral procedure - b) The medic | Novalex | Clinical/Safety Labelling | IB | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | Medium | 2026-06-05 |  |  | 2026-07-22 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-165 | TRG-210 | Change(s) in the Summary of Product Characteristics, Labelling or Package Leaflet intended to implement the outcome of a Union referral procedure - c) The medic | Novalex | Clinical/Safety Labelling | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | High | 2028-12-10 |  |  | 2029-02-04 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-166 | TRG-211 | Change(s) in the Summary of Product Characteristics, Labelling or Package Leaflet of a generic/hybrid/ biosimilar medicinal products following assessment of the | Novalex | Clinical/Safety Labelling | IB | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | Medium | 2026-06-26 |  |  | 2026-08-06 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-167 | TRG-212 | Change(s) in the Summary of Product Characteristics, Labelling or Package Leaflet of a generic/hybrid/ biosimilar medicinal products following assessment of the | Novalex | Clinical/Safety Labelling | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | High | 2029-01-09 |  |  | 2029-06-03 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-168 | TRG-213 | Change(s) in the Summary of Product Character istics, Labelling or Package Leaflet of human medicinal be fulfilled to be supplied products intended to implement the outcome of a procedure concerning PSUR or PASS, or the outcome of the assessment done by the competent authority under Article 45 or 46 of Regulation (EC) No 1901/2006 - a) Implementation of wording agreed by the competent authority | Novalex | Clinical/Safety Labelling | IAIN | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | High | Low/Medium | 2025-07-15 | 2025-07-18 | 2025-08-17 | 2025-07-22 | 2025-07-25 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-169 | TRG-214 | Change(s) in the Summary of Product Characteristics, Labelling or Package Leaflet of human medicinal products intended to implement the outcome of a procedure c | Novalex | Clinical/Safety Labelling | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | High | 2029-02-08 |  |  | 2029-04-15 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-170 | TRG-215 | Change(s) in the Summary of Product Character istics, Labelling or Package Leaflet due to new quality, be fulfilled to be supplied preclinical, clinical or pharmacovigilance data. | Novalex | Pharmacovigilance | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | High | High | 2025-03-01 | 2025-03-03 | 2025-04-13 | 2025-04-17 | 2025-04-21 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-171 | TRG-216 | Change in the legal status of a medicinal product for centrally authorised products - a) For generic/hybrid/biosimilar medicinal products 1, 2 following an appr | Novalex | Clinical/Safety Labelling | IB | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | Medium | 2026-07-17 |  |  | 2026-09-10 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-172 | TRG-217 | Change in the legal status of a medicinal product for centrally authorised products - b) All other legal status changes 1. Attached to the cover letter of the v | Novalex | Clinical/Safety Labelling | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | High | 2029-03-10 |  |  | 2029-10-15 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-173 | TRG-218 | Change(s) to therapeutic indication(s) - a) Addition of a new therapeutic indication or modi fication of an approved one | Novalex | Clinical/Safety Labelling | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | High | 2029-04-09 |  |  | 2029-10-08 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-174 | TRG-219 | Change(s) to therapeutic indication(s) - b) Deletion of a therapeutic indication Note: where the change takes place in the context of | Novalex | Clinical/Safety Labelling | IB | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | Medium | 2026-08-07 |  |  | 2026-10-22 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-175 | TRG-220 | Deletion of: - a) a pharmaceutical form | Novalex | Regulatory | IB |  | Not Started | Medium | Medium | 2026-08-28 |  |  | 2026-10-26 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-176 | TRG-221 | Deletion of: - b) a strength 1, 2 1. Declaration that the remaining product presentation(s) are adequate for | Novalex | Clinical/Safety Labelling | IB | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | Medium | 2026-09-18 |  |  | 2026-11-17 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-177 | TRG-222 | Introduction of, or changes to, a summary of pharmacovigilance system for medicinal products for human be fulfilled to be supplied use (*) - a) Introduction of a summary of pharmacovigilance 1, 2 system, changes in QPPV (including con | Novalex | Pharmacovigilance | II |  | Archived | High | High | 2025-03-15 | 2025-04-03 | 2025-07-16 | 2025-09-04 | 2025-09-24 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-178 | TRG-223 | Change(s) to an existing pharmacovigilance system as described in the detailed description of the pharmacovigilance system (DDPS). - a) Change in the QPPV and/o | Novalex | Pharmacovigilance | IAIN |  | Archived | High | Low/Medium | 2025-02-22 | 2025-02-23 | 2025-03-25 | 2025-02-27 | 2025-02-27 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-179 | TRG-224 | Change(s) to an existing pharmacovigilance system as described in the detailed description of the pharmacovigilance system (DDPS). - b) Change(s) in the safety | Novalex | Pharmacovigilance | IAIN | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | High | Low/Medium | 2025-03-08 | 2025-03-08 | 2025-04-07 | 2025-03-15 | 2025-03-18 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-180 | TRG-225 | Change(s) to an existing pharmacovigilance system as described in the detailed description of the pharmacovigilance system (DDPS). - c) Other change(s) to the D | Novalex | Pharmacovigilance | IA |  | Not Started | High | Low | 2026-06-01 |  |  | 2026-10-06 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-181 | TRG-226 | Change(s) to an existing pharmacovigilance system as described in the detailed description of the pharmacovigilance system (DDPS). - d) Change(s) to a DDPS foll | Novalex | Pharmacovigilance | IAIN |  | Archived | High | Low/Medium | 2025-03-22 | 2025-03-22 | 2025-04-21 | 2025-03-23 | 2025-03-29 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-182 | TRG-227 | Change in the frequency and/or date of submission of periodic safety update reports (PSUR) for human medicinal products | Novalex | Regulatory | IAIN | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | Medium | Low/Medium | 2025-11-11 | 2025-11-14 | 2025-12-14 | 2025-11-15 | 2025-11-19 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-183 | TRG-228 | Introduction of, or change(s) to, the obligations and conditions of a marketing authorisation, including the risk management plan - a) Implementation of wording | Novalex | Regulatory | IAIN | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | Medium | Low/Medium | 2025-04-05 | 2025-04-05 | 2025-05-05 | 2025-04-08 | 2025-04-11 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-184 | TRG-229 | Introduction of, or change(s) to, the obligations and conditions of a marketing authorisation, including be fulfilled to be supplied the risk management plan - b) Implementation of change(s) which require to be further substantiated by new additional da | Novalex | Regulatory | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Archived | High | High | 2025-03-01 | 2025-03-06 | 2025-04-28 | 2025-05-13 | 2025-05-21 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-185 | TRG-230 | Inclusion or deletion of black symbol and explanatory statements for medicinal products in the list of medicinal products that are subject to additional monitor | Novalex | Regulatory | IAIN |  | Archived | Medium | Low/Medium | 2025-04-19 | 2025-04-21 | 2025-05-21 | 2025-04-28 | 2025-04-28 | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-186 | TRG-231 | Other variations not specifically covered elsewhere in this Annex which involve the submission of studies to the competent authority (*) | Novalex | Regulatory | II | DILI/hepatotoxicity signal identified in PSUR No.2; 42 spontaneous reports; SmPC 4.4 and 4.8/RMP update may be relevant | Not Started | High | High | 2029-05-09 |  |  | 2029-10-29 |  | Pharmacovigilance / Safety Regulatory Lead | Yes
NVX-SUB-187 | TRG-269 | change/addition of active substance | Novalex | Regulatory/CMC | Extension |  | Not Started | High | High | 2028-06-01 |  |  | 2029-09-24 |  | Regulatory Affairs Lead with CMC/Clinical/Medical | No
NVX-SUB-188 | TRG-270 | new strength | Novalex | CMC/Clinical | Extension |  | Implementation Overdue | High | High | 2024-08-08 | 2024-10-29 | 2025-08-02 | 2026-01-20 |  | Regulatory Affairs Lead with CMC and Clinical | No
NVX-SUB-189 | TRG-271 | new pharmaceutical form | Novalex | CMC/Clinical | Extension |  | Not Started | High | High | 2027-06-01 |  |  | 2028-11-05 |  | Regulatory Affairs Lead with CMC/Clinical | No
NVX-SUB-190 | TRG-272 | new route of administration | Novalex | Clinical/CMC | Extension |  | Not Started | High | High | 2029-06-01 |  |  | 2030-09-09 |  | Regulatory Affairs Clinical Lead with CMC | No

## Sheet1
Archived
Implementation Overdue
Approved - Pending Implementation
Under Assessment
Implemented