## Gantt chart
| Q1 2018 | Q2 2018 | Q3 2018 | Q4 2018 | Q1 2019 | Q2 2019 | Q3 2019 | Q4 2019 | Q1 2020 | Q2 2020 | Q3 2020 | Q4 2020 | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023 | Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024 | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028 | Q1 2029 | Q2 2029 | Q3 2029 | Q4 2029 | Q1 2030 | Q2 2030 | Q3 2030 | Q4 2030
Discovery / Candidate Selection
API Development
API Characterisation
Pre-formulation
Drug Product Development
Analytical Development
Non-clinical Development
GMP Readiness
Drug Product GMP
Clinical Development
Clinical Pharmacology
Packaging Development
Phase II
Phase II
EU Scientific Advice
Phase III Start
Process Validation Planning
Stability
Commercial Site Readiness
Phase III Completion
MAA Preparation
Quality Finalisation
EU MAA Submission
EMA Assessment
CHMP Opinion
European Commission Decision
Launch Readiness
EU Launch
Pharmacovigilance
Post-approval CMC
Packaging Lifecycle
PSUR No.1
Type IA Annual Update Planning
SUB-004
Post-approval Clinical Safety
PSUR No.2
Signal Validation
SUB-006 Preparation
SUB-006 Submission
Type IA Annual Update
SUB-010 Planning
SUB-006 Assessment
Current Status
Today / Portfolio Cut-off
SUB-010 Submission Target
SUB-006 EC Decision Target
Artwork Implementation
Risk Minimisation Effectiveness
PSUR No.3
Potential Type II
Potential IB/II CMC
Potential Extension
Lifecycle Expansion
Lifecycle Maintenance
Renewal Preparation
Mature Lifecycle

## novalex_eu_timeline_of_events
Timeline ID | Date / Period | Start date | End date | Duration | Lifecycle Stage | Event / Milestone | Regulatory / CMC Meaning | Submission / Procedure Type | Key Documents / Dossier Sections | Functional Owner | Status as of 11 May 2026 | Notes / Portfolio Logic
T-001 | Q1 2018 | 2018-01-01 | 2018-03-31 | 90 | Discovery / Candidate Selection | Novalexib selected as lead EP4 receptor antagonist | Target product profile created for osteoarthritis pain with lower GI risk than NSAIDs | Internal development milestone | Target Product Profile; early non-clinical strategy; early CMC developability report | R&D / Clinical Strategy | Completed | Scientific starting point for the fictional Novalex lifecycle.
T-002 | Q2 2018 | 2018-04-01 | 2018-06-30 | 91 | API Development | Initial synthetic route designed | Five-step convergent synthesis developed from fluoroaniline and pyridine precursors | Internal CMC milestone | Module 3.2.S.2.2 draft; route selection report; impurity risk assessment | CMC / Process Chemistry | Completed | Establishes API route and impurity control strategy.
T-003 | Q3 2018 | 2018-07-01 | 2018-09-30 | 92 | API Characterisation | API physical and chemical characterisation completed | White to off-white crystalline powder; low aqueous solubility identified | Internal CMC milestone | 3.2.S.3.1; 3.2.S.3.2; solubility profile; polymorph screen | Analytical Development | Completed | BCS Class II risk begins to shape CMC strategy.
T-004 | Q4 2018 | 2018-10-01 | 2018-12-31 | 92 | Pre-formulation | BCS Class II risk confirmed | Low solubility and high permeability confirm dissolution as a critical quality attribute | Internal CMC milestone | Pre-formulation report; particle size strategy; dissolution method strategy | Formulation / Analytical Development | Completed | Justifies tight particle-size and dissolution controls.
T-005 | Q1 2019 | 2019-01-01 | 2019-03-31 | 90 | Drug Product Development | Film-coated tablet concept selected | Immediate-release oral film-coated tablets selected for 25 mg and 50 mg strengths | Internal CMC milestone | 3.2.P.1; 3.2.P.2; excipient compatibility studies | Formulation Development | Completed | Tablet platform selected with MCC, lactose, croscarmellose sodium, magnesium stearate, colloidal silicon dioxide and Opadry II coating.
T-006 | Q2 2019 | 2019-04-01 | 2019-06-30 | 91 | Analytical Development | Dissolution method developed | Dissolution method positioned as surrogate for bioavailability due to BCS Class II behavior | Internal CMC milestone | 3.2.P.5.2; 3.2.P.5.3; dissolution validation; discriminatory method report | Analytical Development | Completed | Important for later formulation, process and site changes.
T-007 | Q3 2019 | 2019-07-01 | 2019-09-30 | 92 | Non-clinical Development | GLP toxicology package initiated | Non-clinical safety package started to support first-in-human dosing | CTA / IND-enabling package | Module 4 toxicology reports; safety pharmacology; genotoxicity | Non-clinical / Toxicology | Completed | Can include hepatic monitoring as a point of attention.
T-008 | Q4 2019 | 2019-10-01 | 2019-12-31 | 92 | GMP Readiness | API pilot-scale GMP batch manufactured | Clinical API material generated for early clinical studies | Internal GMP milestone | Batch records; certificate of analysis; impurity profile; stability protocol | CMC / QA | Completed | Original API manufacturer: Chembridgx Synthesis GmbH, Frankfurt, Germany.
T-009 | Q1 2020 | 2020-01-01 | 2020-03-31 | 91 | Drug Product GMP | Clinical tablet batches manufactured | 25 mg and 50 mg clinical film-coated tablet batches manufactured and released | Internal GMP milestone | 3.2.P.3.3 draft; batch records; certificate of analysis; release specifications | Drug Product Manufacturing / QA | Completed | Wet granulation, drying, milling, blending, compression, film coating and packaging process established.
T-010 | Q2 2020 | 2020-04-01 | 2020-06-30 | 91 | Clinical Development | Phase I SAD/MAD study completed | Safety, tolerability, PK and dose proportionality established | Clinical trial milestone | Module 5 clinical study report; PK report; investigator brochure update | Clinical / Clinical Pharmacology | Completed | Supports once-daily dosing based on approximately 14-hour half-life.
T-011 | Q3 2020 | 2020-07-01 | 2020-09-30 | 92 | Clinical Pharmacology | Food-effect and DDI planning completed | Food flexibility and CYP interaction risks assessed | Clinical pharmacology milestone | Food-effect protocol; DDI protocol; 2.7.2 clinical pharmacology summary | Clinical Pharmacology | Completed | Supports later SmPC language on dosing with or without food and CYP3A4/CYP2C9 interaction management.
T-012 | Q4 2020 | 2020-10-01 | 2020-12-31 | 92 | Packaging Development | PVC/PVDC-aluminium blister selected | Moisture-protective blister packaging selected for commercial product | Internal CMC milestone | 3.2.P.7; packaging compatibility; extractables/leachables justification | Packaging / CMC | Completed | Primary packaging selected for 14, 28 and 56 tablet pack sizes.
T-013 | Q1 2021 | 2021-01-01 | 2021-03-31 | 90 | Phase II | NOVA-201 initiated | Dose-finding study in adults with knee osteoarthritis initiated | Clinical trial milestone | Protocol; Investigator Brochure; IMPD; CTA documents | Clinical Operations | Completed | Arms: 10 mg, 25 mg, 50 mg and placebo over 12 weeks.
T-014 | Q3 2021 | 2021-07-01 | 2021-09-30 | 92 | Phase II | NOVA-201 completed | 25 mg and 50 mg selected for Phase III development | Clinical development milestone | Clinical study report; dose selection memo; statistical outputs | Clinical / Biostatistics | Completed | 10 mg did not separate from placebo; 25 mg and 50 mg showed meaningful WOMAC pain improvement.
T-015 | Q4 2021 | 2021-10-01 | 2021-12-31 | 92 | EU Scientific Advice | EMA scientific advice sought | EMA advice obtained on Phase III endpoints, comparator, safety database and regulatory strategy | Scientific advice | EMA briefing package; questions to EMA; meeting minutes | Regulatory Strategy | Completed | Shows proactive EU regulatory planning for the portfolio.
T-016 | Q1 2022 | 2022-01-01 | 2022-03-31 | 90 | Phase III Start | NOVA-301 initiated | Pivotal Phase III placebo- and active-controlled trial begins | Clinical trial milestone | Protocol; SAP; CTA; IMPD update | Clinical Operations | Completed | Study includes knee and hip OA; placebo and naproxen active comparator.
T-017 | Q2 2022 | 2022-04-01 | 2022-06-30 | 91 | Process Validation Planning | Commercial process validation strategy approved | Commercial wet granulation and tablet manufacturing control strategy finalised | Internal CMC milestone | PPQ protocol; control strategy; process risk assessment | CMC / MSAT / QA | Completed | Prepares Module 3 commercial manufacturing section.
T-018 | Q3 2022 | 2022-07-01 | 2022-09-30 | 92 | Stability | Primary stability programme initiated | Stability programme started to support proposed shelf life and storage conditions | Internal CMC milestone | 3.2.P.8.1; 3.2.P.8.2; stability protocols | Stability / QA | Completed | Initial stability package later supports approval and shelf-life extension.
T-019 | Q4 2022 | 2022-10-01 | 2022-12-31 | 92 | Commercial Site Readiness | NovaTech Pharma Ltd, Cork confirmed as DP manufacturing and packaging site | EU-based finished product manufacture and packaging chain locked | Internal CMC / GMP milestone | Site master file; MIA/GMP evidence; manufacturing flow chart | CMC / QA / Supply Chain | Completed | Commercial DP manufacturing and packaging site established in Ireland.
T-020 | Q1 2023 | 2023-01-01 | 2023-03-31 | 90 | Phase III Completion | NOVA-301 completed | Pivotal efficacy and safety dataset locked | Clinical milestone | CSR; statistical outputs; integrated safety and efficacy inputs | Clinical / Biostatistics | Completed | Positive WOMAC pain results with lower GI adverse events than naproxen; ALT/AST elevations observed in novalexib arms.
T-021 | Q2 2023 | 2023-04-01 | 2023-06-30 | 91 | MAA Preparation | EU MAA dossier compilation begins | CTD Modules 1 to 5 compiled for initial EU approval | Centralised MAA preparation | Module 1-5; RMP; product information; mock-ups | Regulatory Affairs | Completed | Start of formal EU submission readiness phase.
T-022 | Q3 2023 | 2023-07-01 | 2023-09-30 | 92 | Quality Finalisation | Commercial specifications finalised | API and finished product specifications locked for the MAA | MAA CMC readiness | 3.2.S.4; 3.2.P.5; method validation; batch analysis | CMC / Analytical / QA | Completed | Includes assay, impurities, degradation products and dissolution controls.
T-023 | Q4 2023 | 2023-10-01 | 2023-12-31 | 92 | EU MAA Submission | Initial MAA submitted to EMA | First EU authorisation application filed through the centralised procedure | Centralised MAA | eCTD sequence 0000; Module 1-5; RMP; PI | Regulatory Affairs | Completed | Main initial registration milestone.
T-024 | Q1 2024 | 2024-01-01 | 2024-03-31 | 91 | EMA Assessment | Day 120 List of Questions received | CHMP questions received on CMC, clinical safety, hepatic enzyme elevations and RMP | Centralised MAA assessment | Responses to LoQ; updated Module 2; Module 3 clarifications; RMP update | Regulatory / CMC / Clinical / PV | Completed | Cross-functional response management milestone.
T-025 | Q2 2024 | 2024-04-01 | 2024-06-30 | 91 | EMA Assessment | Day 180 List of Outstanding Issues resolved | Remaining regulatory issues closed before CHMP opinion | Centralised MAA assessment | Responses to LoOI; final PI negotiation; updated RMP | Regulatory Affairs | Completed | Can include negotiated hepatic monitoring language.
T-026 | 2026-07-24 | 2026-07-24 | 2024-08-31 | 31 | CHMP Opinion | Positive CHMP opinion issued | CHMP recommends EU approval of Novalex | Centralised MAA opinion | Final assessment report; final English PI; RMP | Regulatory Affairs | Completed | Scientific approval before EC decision.
T-027 | 2026-09-24 | 2026-09-24 | 2024-09-30 | 30 | European Commission Decision | EU Marketing Authorisation granted | Novalex authorised in the EU | Centralised MA | Commission Decision; Annex I; Annex II; Annex IIIA; Annex IIIB; Annex A | Regulatory Affairs | Approved | Initial indication: symptomatic relief of mild to moderate pain associated with OA of the knee and hip in adults.
T-028 | 2026-10-24 | 2026-10-24 | 2024-10-31 | 31 | Launch Readiness | First EU batch release | QP release and supply chain activation completed | Commercial launch milestone | Batch release documentation; QP certification; launch checklist | QA / Supply Chain | Completed | Commercial supply begins.
T-029 | 2026-11-24 | 2026-11-24 | 2024-11-30 | 30 | EU Launch | Novalex launched in Ireland | First commercial placing on the EU market | Post-authorisation commercial milestone | Launch notification; marketing status update if applicable | Regulatory / Commercial | Completed | Irish MAH and Irish manufacturing setup make this portfolio geography realistic.
T-030 | 2026-12-24 | 2026-12-24 | 2024-12-31 | 31 | Pharmacovigilance | First post-launch safety review completed | Routine post-marketing safety monitoring begins | Routine PV | Safety database review; signal detection report | Pharmacovigilance | Completed | Baseline for later DILI signal narrative.
T-031 | 2026-01-25 | 2026-01-25 | 2025-01-31 | 31 | Post-approval CMC | Minor editorial update to Module 3 assessed | Administrative or formatting correction after approval | Type IA or no variation depending content | Module 3 editorial table; eAF if variation required | Regulatory CMC | Completed | If approved dossier text changes, include as variation; if purely non-substantive, document internally.
T-032 | 2026-03-25 | 2026-03-25 | 2025-03-31 | 31 | Packaging Lifecycle | 56-tablet pack operational readiness completed | Commercial readiness for 2-month pack supply confirmed | Type IA/IAIN/IB depending approved pack status | Annex A; PI; 3.2.P.7; packaging specifications | Regulatory CMC / Packaging | Completed | Current packaging includes 14, 28 and 56 tablet pack sizes.
T-033 | 2026-06-25 | 2026-06-25 | 2025-06-30 | 30 | PSUR No.1 | First PSUR submitted | Routine post-authorisation benefit-risk review completed | PSUR procedure | PSUR; signal summary; exposure estimate | PV / Regulatory Safety | Completed | No major regulatory action yet; hepatic enzyme elevations remain under monitoring.
T-034 | 2026-07-25 | 2026-07-25 | 2025-07-31 | 31 | Type IA Annual Update Planning | IA annual update cycle prepared | Eligible minor IA changes collected for annual update | Type IA annual update planning | Cover letter; eAF; precise scope; present/proposed table | Regulatory Operations | Completed | IA changes not requiring immediate notification are normally collected into annual updates.
T-035 | 2026-09-25 | 2026-09-25 | 2025-09-30 | 30 | SUB-004 | Shelf-life extension approved and implemented | Shelf life extended to 36 months | Variation, likely Type IB or Type II depending data and exact classification | 3.2.P.8.1; 3.2.P.8.2; 3.2.P.8.3; updated PI if impacted | CMC / Stability / Regulatory | Approved | Current Novalex shelf life is 36 months.
T-036 | 2026-10-25 | 2026-10-25 | 2025-10-31 | 31 | Post-approval Clinical Safety | Hepatic safety signal under surveillance | Elevated ALT/AST pattern reviewed internally | Signal management, not yet variation | Signal evaluation report; cumulative safety review | Pharmacovigilance | Completed | Links to Phase III ALT/AST elevations.
T-037 | 2026-12-25 | 2026-12-25 | 2025-12-31 | 31 | PSUR No.2 | DILI cluster detected | 42 spontaneous DILI reports identified in EudraVigilance | PSUR / signal detection | PSUR No.2; signal validation; case narratives; exposure calculation | Pharmacovigilance | Completed | 42 confirmed DILI cases across approximately 280,000 patient-years; classified as rare.
T-038 | 2026-01-26 | 2026-01-26 | 2026-01-31 | 31 | Signal Validation | DILI signal confirmed as probable | Medical safety team and external hepatologist conclude probable causality | Signal management | Signal validation report; Bradford Hill causality assessment; benefit-risk memo | PV / Medical Safety | Completed | Primary regulatory trigger for Type II safety variation SUB-006.
T-039 | 2026-01-26 | 2026-01-26 | 2026-01-31 | 31 | SUB-006 Preparation | Type II safety variation drafted | SmPC, PIL and RMP update prepared for DILI identified risk | Type II C-category safety variation | SmPC 4.4; SmPC 4.8; PIL; RMP Part II Module SVII; RMP Part V | Regulatory Safety / PV | Completed | Adds hepatotoxicity warning and rare DILI adverse reaction.
T-040 | 2026-02-26 | 2026-02-26 | 2026-02-28 | 28 | SUB-006 Submission | DILI Type II variation submitted to EMA | Formal EU label and RMP update submitted | Type II variation | eAF; cover letter; clinical overview addendum; RMP; PI tracked changes | Regulatory Affairs / PV | Submitted | DHPC not required in this fictional narrative; routine risk minimisation considered sufficient.
T-041 | 2026-03-26 | 2026-03-26 | 2026-03-31 | 31 | Type IA Annual Update | Minor IA annual update submitted | Eligible minor implemented changes consolidated | Type IA annual update | eAF; precise scope; present/proposed table; supporting documents | Regulatory Operations | Submitted / Completed | EMA reviews Type IA/IAIN notifications within 30 days.
T-042 | 2026-03-26 | 2026-03-26 | 2026-03-31 | 31 | SUB-010 Planning | New API manufacturer qualification begins | Synthia Pharma AG, Zurich proposed as additional or replacement API manufacturer | Quality variation planning | 3.2.S.2.1-3.2.S.2.6; GMP/QP declarations; batch analysis; stability | CMC / Supplier Quality | In Progress | Potential variation depends on route, impurity profile and comparability data.
T-043 | 2026-04-26 | 2026-04-26 | 2026-04-30 | 30 | SUB-006 Assessment | EMA/CHMP assessment of DILI variation ongoing | Questions or clarifications handled during Type II review | Type II assessment | Response package; updated PI/RMP if requested | Regulatory Safety / PV | Pending Health Authority | High-priority safety variation.
T-044 | 2026-05-26 | 2026-05-26 | 2026-05-31 | 31 | Current Status | SmPC v4.0 updated for DILI pending EC Decision | Scientific position agreed or near-agreed; legal MA update pending | Type II post-opinion / EC decision stage | Final PI; RMP; annexes | Regulatory Affairs | Pending EC Decision | Current as of 11 May 2026.
T-045 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 1 | Today / Portfolio Cut-off | Current lifecycle snapshot recorded | Tracker status date for Novalex project | Internal tracker milestone | Submission tracker; regulatory trigger log; variation register | Regulatory Operations | Current | Use this as the as-of date in Power BI/dashboard.
T-046 | 2026-06-26 | 2026-06-26 | 2026-06-30 | 30 | SUB-010 Submission Target | API manufacturer variation submission planned | Add or replace Synthia Pharma AG as API manufacturer | Type IB or Type II depending change impact | 3.2.S; QP declaration; batch analysis; impurity comparison; stability commitment | Regulatory CMC / Supplier Quality | Planned | If synthetic route or impurity profile significantly changes, classification may increase to Type II.
T-047 | 2026-07-26 | 2026-07-26 | 2026-07-31 | 31 | SUB-006 EC Decision Target | EC decision expected for DILI update | Legal update to MA annexes completed | Type II closure | Commission Decision; final PI all EU languages; final RMP | Regulatory Affairs | Planned | Implementation of updated safety wording begins after EC decision.
T-048 | 2026-08-26 | 2026-08-26 | 2026-08-31 | 31 | Artwork Implementation | DILI label implemented in packaging | Updated PIL and safety wording enter commercial artwork cycle | Post-approval implementation | Artwork change control; packaging component specifications; QA release | Regulatory / Artwork / QA | Planned | Safety labelling change required.
T-049 | 2026-09-26 | 2026-09-26 | 2026-09-30 | 30 | Risk Minimisation Effectiveness | First post-DILI label effectiveness check | Monitor whether LFT monitoring language is understood and implemented | RMP follow-up | RMP effectiveness metrics; PV signal report | PV / Medical Affairs | Planned | Supports routine risk minimisation sufficiency.
T-050 | Q4 2026 | 2026-10-01 | 2026-12-31 | 92 | PSUR No.3 | Next PSUR after DILI update | Evaluate DILI reporting after label and RMP update | PSUR | PSUR; interval and cumulative cases; benefit-risk evaluation | Pharmacovigilance | Planned | Shows full PV lifecycle follow-up.
T-051 | Q1 2027 | 2027-01-01 | 2027-03-31 | 90 | Potential Type II | Hepatic impairment wording refinement | Additional PK or safety data may justify modified dose advice | Type II safety/clinical variation | SmPC 4.2; 4.4; 4.8; 5.2; clinical overview addendum | Clinical Pharmacology / PV | Planned | Relevant because novalexib is hepatically metabolised via CYP3A4 and CYP2C9.
T-052 | Q2 2027 | 2027-04-01 | 2027-06-30 | 91 | Potential IB/II CMC | Dissolution specification tightening | Improve control of BCS Class II product performance | Type IA/IB/II depending scope | 3.2.P.5.1; 3.2.P.5.2; validation; dissolution trend data | CMC / Analytical | Planned | Dissolution is a critical quality attribute for Novalex.
T-053 | Q3 2027 | 2027-07-01 | 2027-09-30 | 92 | Potential Extension | New 75 mg strength feasibility assessment | Higher-strength development assessed; may raise safety and dose concerns | Extension or Type II depending strategy | 3.2.P; BE study; clinical safety justification; PI update | Regulatory Strategy / Clinical / CMC | Planned / Optional | Current maximum daily dose is 50 mg, so 75 mg would be high-risk.
T-054 | Q4 2027 | 2027-10-01 | 2027-12-31 | 92 | Lifecycle Expansion | New indication feasibility: hand osteoarthritis | Clinical development strategy for additional OA population | Type II C.6 if submitted | Clinical protocol; RMP update; SmPC/PIL update | Clinical Strategy / Regulatory | Planned / Optional | New or modified therapeutic indication normally requires Type II variation.
T-055 | 2028 | 2028-01-01 | 2028-12-31 | 366 | Lifecycle Maintenance | Manufacturing process optimisation | Scale-up or process parameter optimisation at NovaTech Cork | Type IA/IB/II depending risk | 3.2.P.3.3; 3.2.P.3.4; process validation; dissolution comparison | MSAT / CMC / QA | Future | Solid oral process changes may need dissolution comparison and BE justification.
T-056 | 2028 | 2028-01-01 | 2028-12-31 | 366 | Lifecycle Maintenance | Alternative blister material assessment | Improve moisture protection or supply resilience | Type IA/IB/II depending packaging impact | 3.2.P.7; 3.2.P.8; packaging specifications; stability | Packaging / CMC | Future | Packaging changes generally need stability and compatibility evidence.
T-057 | 2029 | 2029-01-01 | 2029-12-31 | 365 | Renewal Preparation | EU renewal dossier planning | Long-term lifecycle renewal preparation if applicable | Renewal | Consolidated quality/safety/efficacy review; PSUR history; RMP; PI | Regulatory Affairs / PV | Future | Useful for long-term lifecycle management story.
T-058 | 2029-2030 | 2029-01-01 | 2030-12-31 | 730 | Mature Lifecycle | Generic-readiness and competitive monitoring | Prepare for market competition and manage post-approval commitments | Internal lifecycle strategy | Patent and exclusivity tracker; variation history; commitments register | Regulatory Strategy | Future | Not a variation itself but useful for regulatory operations realism.

## Sheet2
Task | Start Quarter | End Quarter | Start Date | End Date | Category | Status | Milestone
Discovery / Candidate Selection | Q1 2018 | Q4 2018 | 2018-01-01 | 2018-12-31 | Discovery & Research | Completed | No
API Development | Q3 2018 | Q2 2020 | 2018-07-01 | 2020-06-30 | CMC Development | Completed | No
API Characterisation | Q4 2018 | Q4 2020 | 2018-10-01 | 2020-12-31 | CMC Development | Completed | No
Pre-formulation | Q1 2019 | Q3 2020 | 2019-01-01 | 2020-09-30 | CMC Development | Completed | No
Drug Product Development | Q2 2019 | Q2 2021 | 2019-04-01 | 2021-06-30 | CMC Development | Completed | No
Analytical Development | Q2 2019 | Q2 2021 | 2019-04-01 | 2021-06-30 | CMC Development | Completed | No
Non-clinical Development | Q2 2019 | Q4 2020 | 2019-04-01 | 2020-12-31 | Non-clinical Development | Completed | No
Clinical Development | Q1 2020 | Q4 2021 | 2020-01-01 | 2021-12-31 | Clinical Development | Completed | No
Clinical Pharmacology | Q1 2020 | Q2 2021 | 2020-01-01 | 2021-06-30 | Clinical Development | Completed | No
GMP Readiness | Q2 2020 | Q2 2021 | 2020-04-01 | 2021-06-30 | Manufacturing & GMP | Completed | No
Drug Product GMP | Q3 2020 | Q2 2021 | 2020-07-01 | 2021-06-30 | Manufacturing & GMP | Completed | No
Packaging Development | Q3 2020 | Q2 2021 | 2020-07-01 | 2021-06-30 | Packaging & Artwork | Completed | No
Phase I | Q1 2020 | Q4 2020 | 2020-01-01 | 2020-12-31 | Clinical Development | Completed | No
Phase II | Q1 2021 | Q3 2021 | 2021-01-01 | 2021-09-30 | Clinical Development | Completed | No
Phase III Start | Q2 2021 | Q2 2021 | 2021-04-01 | 2021-06-30 | Clinical Development | Completed | Yes
Phase III Completion | Q4 2021 | Q4 2021 | 2021-10-01 | 2021-12-31 | Clinical Development | Completed | Yes
EU Scientific Advice | Q2 2020 | Q3 2020 | 2020-04-01 | 2020-09-30 | Regulatory Strategy | Completed | Yes
Process Validation Planning | Q1 2021 | Q2 2021 | 2021-01-01 | 2021-06-30 | CMC Development | Completed | No
Process Validation Completion | Q2 2021 | Q3 2021 | 2021-04-01 | 2021-09-30 | CMC Development | Completed | Yes
Stability Package Finalisation | Q1 2021 | Q3 2021 | 2021-01-01 | 2021-09-30 | CMC Stability | Completed | No
Commercial Site Readiness | Q2 2021 | Q4 2021 | 2021-04-01 | 2021-12-31 | Manufacturing & GMP | Completed | No
Quality Finalisation | Q2 2021 | Q3 2021 | 2021-04-01 | 2021-09-30 | Quality / CMC | Completed | No
MAA Preparation | Q1 2021 | Q3 2021 | 2021-01-01 | 2021-09-30 | Regulatory Submission | Completed | No
EU MAA Submission | Q3 2021 | Q3 2021 | 2021-09-15 | 2021-09-15 | Regulatory Submission | Completed | Yes
EMA Validation | Q3 2021 | Q4 2021 | 2021-09-16 | 2021-10-15 | EMA Review | Completed | Yes
EMA Assessment | Q4 2021 | Q1 2022 | 2021-10-16 | 2022-02-28 | EMA Review | Completed | No
CHMP Opinion | Q1 2022 | Q1 2022 | 2022-02-24 | 2022-02-24 | EMA Review | Completed | Yes
European Commission Decision / MAA Approval | Q1 2022 | Q1 2022 | 2022-03-15 | 2022-03-15 | Approval | Completed | Yes
EU Launch Readiness | Q1 2022 | Q2 2022 | 2022-03-16 | 2022-06-30 | Commercial Launch | Completed | No
EU Launch | Q2 2022 | Q4 2022 | 2022-04-01 | 2022-12-31 | Commercial Launch | Completed | Yes
Post-authorisation Pharmacovigilance | Q1 2022 | Q4 2030 | 2022-03-15 | 2030-12-31 | Post-Approval Safety | Ongoing | No
Post-approval CMC Lifecycle | Q2 2022 | Q4 2030 | 2022-04-01 | 2030-12-31 | Post-Approval CMC | Ongoing | No
Packaging Lifecycle | Q2 2022 | Q4 2030 | 2022-04-01 | 2030-12-31 | Packaging & Artwork | Ongoing | No
Lifecycle Maintenance | Q2 2022 | Q4 2030 | 2022-04-01 | 2030-12-31 | Strategic Lifecycle | Ongoing | No
First Post-authorisation Variation - MAH Name/Address Change | Q2 2024 | Q2 2024 | 2024-06-15 | 2024-06-15 | Post-Approval Variation | Completed | Yes
Type IA Annual Update Planning | Q4 2024 | Q1 2025 | 2024-10-01 | 2025-03-31 | Post-Approval Variation | Completed | No
SUB-004 Preparation | Q1 2025 | Q1 2025 | 2025-01-01 | 2025-03-31 | Post-Approval Submission | Completed | No
SUB-004 Submission | Q1 2025 | Q1 2025 | 2025-03-20 | 2025-03-20 | Post-Approval Submission | Completed | Yes
Type IA Annual Update | Q1 2025 | Q2 2025 | 2025-01-01 | 2025-06-30 | Post-Approval Variation | Completed | Yes
PSUR No.1 | Q2 2025 | Q2 2025 | 2025-04-01 | 2025-06-30 | Post-Approval Safety | Completed | Yes
Post-approval Clinical Safety Review | Q2 2025 | Q4 2030 | 2025-04-01 | 2030-12-31 | Post-Approval Safety | Ongoing | No
Signal Validation | Q3 2025 | Q3 2025 | 2025-07-01 | 2025-09-30 | Post-Approval Safety | Completed | Yes
SUB-006 Preparation | Q3 2025 | Q3 2025 | 2025-07-01 | 2025-09-30 | Post-Approval Submission | Completed | No
SUB-006 Submission | Q3 2025 | Q3 2025 | 2025-09-15 | 2025-09-15 | Post-Approval Submission | Completed | Yes
SUB-006 Assessment | Q4 2025 | Q1 2026 | 2025-10-01 | 2026-03-31 | EMA Review | Completed | No
SUB-006 EC Decision | Q1 2026 | Q1 2026 | 2026-03-15 | 2026-03-15 | Approval | Completed | Yes
SUB-006 Implementation | Q1 2026 | Q2 2026 | 2026-03-16 | 2026-06-30 | Packaging & Artwork | In Progress | Yes
SUB-010 Planning | Q1 2026 | Q2 2026 | 2026-01-01 | 2026-06-30 | Post-Approval Submission | In Progress | No
SUB-010 Submission Target | Q3 2026 | Q3 2026 | 2026-07-15 | 2026-07-15 | Post-Approval Submission | Planned | Yes
SUB-010 Assessment | Q3 2026 | Q4 2026 | 2026-07-16 | 2026-12-31 | EMA Review | Planned | No
SUB-010 EC Decision Target | Q1 2027 | Q1 2027 | 2027-01-31 | 2027-01-31 | Approval | Planned | Yes
Current Status | Q2 2026 | Q2 2026 | 2026-04-01 | 2026-06-30 | Portfolio Checkpoint | Current | Yes
Today / Portfolio Cutoff | Q2 2026 | Q2 2026 | 2026-05-26 | 2026-05-26 | Portfolio Checkpoint | Current | Yes
PSUR No.2 | Q2 2026 | Q2 2026 | 2026-04-01 | 2026-06-30 | Post-Approval Safety | In Progress | Yes
Risk Minimisation Effectiveness | Q2 2026 | Q4 2026 | 2026-04-01 | 2026-12-31 | Post-Approval Safety | In Progress | No
Type II CMC Variation Planning | Q2 2026 | Q4 2026 | 2026-04-01 | 2026-12-31 | Post-Approval Variation | In Progress | No
Potential Type II | Q2 2026 | Q4 2030 | 2026-04-01 | 2030-12-31 | Post-Approval Variation | Planned | No
Potential IB/II CMC | Q3 2026 | Q4 2030 | 2026-07-01 | 2030-12-31 | Post-Approval CMC | Planned | No
Potential Extension | Q3 2027 | Q4 2030 | 2027-07-01 | 2030-12-31 | Post-Approval Extension | Planned | No
Renewal Preparation | Q2 2026 | Q1 2027 | 2026-04-01 | 2027-03-31 | Regulatory Maintenance | In Progress | No
EU Renewal Submission | Q1 2027 | Q1 2027 | 2027-01-15 | 2027-01-15 | Regulatory Maintenance | Planned | Yes
Renewal Assessment | Q1 2027 | Q2 2027 | 2027-01-16 | 2027-06-30 | EMA Review | Planned | No
Renewal Approval | Q3 2027 | Q3 2027 | 2027-07-15 | 2027-07-15 | Approval | Planned | Yes
PSUR No.3 | Q2 2027 | Q2 2027 | 2027-04-01 | 2027-06-30 | Post-Approval Safety | Planned | Yes
Lifecycle Expansion | Q2 2028 | Q4 2030 | 2028-04-01 | 2030-12-31 | Strategic Lifecycle | Planned | No
Mature Lifecycle | Q4 2030 | Q4 2030 | 2030-10-01 | 2030-12-31 | Strategic Lifecycle | Planned | Yes